| Français |  |
| --- | --- |

chapter 24

An Act to amend the Construction Lien Act

Assented to December 12, 2017

Her Majesty, by and with the advice and consent of the Legislative Assembly of the Province of Ontario, enacts as follows:

1 The short title of the Construction Lien Act is repealed and the following substituted:

Construction Act

2 (1) Subsection 1 (1) of the Act is amended by adding the following definition:

“broader public sector organization” has the same meaning as in the Broader Public Sector Accountability Act, 2010; (“organisme du secteur parapublic”)

(2) The definition of “construction trade newspaper” in subsection 1 (1) of the Act is repealed.

(3) The definition of “contractor” in subsection 1 (1) of the Act is amended by adding “and includes a joint venture entered into for the purposes of an improvement or improvements” at the end.

(4) The French version of the definition of “home buyer” in subsection 1 (1) of the Act is amended by striking out “un local qui constitue” in the portion before clause (a) and substituting “des lieux qui constituent”.

(5) Clause (a) of the definition of “improvement” in subsection 1 (1) of the Act is amended by adding “capital” before “repair”.

(6) The French version of the definition of “interest in the premises” in subsection 1 (1) of the Act is amended by striking out “intérêt sur le local” and substituting “intérêt sur les lieux”, by striking out “locaux” and substituting “lieux” and by striking out “un local” and substituting “des lieux”.

(7)  Subsection 1 (1) of the Act is amended by adding the following definition:

“monetary supplementary benefit” includes any contribution, remittance, union dues, deduction, payment or other additional compensation of any kind; (“avantage pécuniaire supplémentaire”)

(8)  The definition of “municipality” in subsection 1 (1) of the Act is repealed and the following substituted:

“municipality” means,

(a)	a municipality within the meaning of the Municipal Act, 2001, and

(b)	a local board within the meaning of the Municipal Act, 2001 or the City of Toronto Act, 2006; (“municipalité”)

(9) The definition of “payer” in subsection 1 (1) of the Act is amended by striking out “materials or services” and substituting “services or materials”.

(10) The French version of the definition of “premises” in subsection 1 (1) of the Act is amended by striking out “local” and substituting “lieux”.

(11) Subsection 1 (1) of the Act is amended by adding the following definition:

“prescribed” means prescribed by the regulations; (“prescrit”)

(12) The definition of “price” in subsection 1 (1) of the Act is repealed and the following substituted:

“price” means,

(a)	the contract or subcontract price,

(i)	agreed on between the parties, or

(ii)	if no specific price has been agreed on between them, the actual market value of the services or materials that have been supplied to the improvement under the contract or subcontract, and

(b)	any direct costs incurred as a result of an extension of the duration of the supply of services or materials to the improvement for which the contractor or subcontractor, as the case may be, is not responsible; (“prix”)

(13) Subsection 1 (1) of the Act is amended by adding the following definition:

“regulations” means the regulations made under this Act; (“règlements”)

(14) The definition of “subcontractor” in subsection 1 (1) of the Act is amended by adding “and includes a joint venture entered into for the purposes of an improvement or improvements” at the end.

(15) The French version of the definition of “written notice of a lien” in subsection 1 (1) of the Act is amended by striking out “l’avis d’un privilège” in the portion before clause (a) and substituting “la revendication de privilège”.

(16) The definition of “written notice of a lien” in subsection 1 (1) of the Act is repealed and the following substituted:

“written notice of a lien” means a written notice of a lien in the prescribed form, given by a person having a lien. (“avis écrit d’un privilège”)

(17) Section 1 of the Act is amended by adding the following subsections:

Capital repair

(1.1) For the purposes of clause (a) of the definition of “improvement” in subsection (1), a capital repair to land is any repair intended to extend the normal economic life of the land or of any building, structure or works on the land, or to improve the value or productivity of the land, building, structure or works, but does not include maintenance work performed in order to prevent the normal deterioration of the land, building, structure or works or to maintain the land, building, structure or works in a normal, functional state.

Direct costs

(1.2) For the purposes of clause (b) of the definition of “price” in subsection (1), the direct costs incurred are the reasonable costs of performing the contract or subcontract during the extended period of time, including costs related to the additional supply of services or materials (including equipment rentals), insurance and surety bond premiums, and costs resulting from seasonal conditions, that, but for the extension, would not have been incurred, but do not include indirect damages suffered as a result, such as loss of profit, productivity or opportunity, or any head office overhead costs.

3 (1)  The Act is amended by adding the following section:

Alternative financing and procurement arrangements

1.1  (1)  This section applies if the Crown, a municipality or a broader public sector organization, as the owner of a premises, enters into a project agreement with a special purpose entity that requires the entity to finance and undertake an improvement on behalf of the Crown, municipality or broader public sector organization, as the case may be, and, for the purpose, to enter into an agreement with a contractor in respect of the improvement.

Application of Act, regulations

(2)  Except as provided by this section, this Act and the regulations apply, with the modifications set out in this section and any other necessary modifications,

(a)	to a project agreement between the Crown, a municipality or a broader public sector organization and a special purpose entity as if the project agreement were a contract and the special purpose entity were the contractor; and

(b)	to the agreement between the special purpose entity and the contractor as if the agreement were a subcontract made under the contract.

Specified modifications, Part IV

(3)  For the purposes of section 22, holdback amounts shall be determined in reference to the agreement between the special purpose entity and the contractor.

Specified modifications, Part XI.1

(4)  Section 85.1 applies with the following modifications:

1.	The agreement between the special purpose entity and the contractor is deemed, for the purposes of the section, to be a public contract between the Crown, municipality or broader public sector organization, as the case may be, and the contractor.

2.	The Crown, municipality or broader public sector organization, as the case may be, may require a coverage limit other than one specified in clause 85.1 (4) (b) or (5) (b), provided that it meets or exceeds any coverage limit that may be prescribed for the purposes of this paragraph.

3.	Paragraph 2 does not apply unless the bonds required under subsections 85.1 (4) and (5) and any other security required by the Crown, municipality or broader public sector organization, as the case may be, taken together, reflect an appropriate balance between the adequacy of the security required to ensure the payment of persons supplying services or materials under the public contract on the one hand and the cost of the security on the other.

Where entity deemed to be owner

(5)  The special purpose entity is deemed to be the owner of the premises in place of the Crown, municipality or broader public sector organization, and the agreement between the special purpose entity and the contractor is deemed to be the contract, for the purposes of the following portions and provisions of this Act and any regulations made for the purposes of them and, for the purpose, the portions, provisions and regulations apply with such modifications as may be prescribed and any other necessary modifications:

1.	Subsections 2 (1) and (2).

2.	Section 31.

3.	Section 32.

4.	Section 33.

5.	Section 39.

6.	Any other portion or provision that may be prescribed.

Interpretation, substantial performance of a contract

(6)  For the purposes of subsection (5), a reference in this Act or the regulations to the substantial performance of a contract, as it applies in relation to a project agreement, shall be read as a reference to the substantial performance of the agreement between the special purpose entity and the contractor, subject to any exceptions that may be prescribed.

(2)  Section 1.1 of the Act, as enacted by subsection (1), is amended by adding the following subsections:

Specified modifications, Part I.1

(2.1)  Part I.1 applies with the following modifications:

1.	The Part does not apply with respect to any portion of a project agreement that provides for the operation or maintenance of the improvement by the special purpose entity, or to any portion of an agreement between the special purpose entity and the contractor or any other subcontract made under the project agreement that pertains to the operation or maintenance of the improvement by the special purpose entity.

2.	Subsection 6.3 (2) does not apply, and nothing in the Part shall be read as preventing the inclusion, in a project agreement or agreement between a special purpose entity and a contractor, of a provision requiring certification or approval prior to the giving of a proper invoice.

Specified modifications, Part II.1

(2.2)  Part II.1 applies with the following modifications:

1.	The following matters may not be the subject of an adjudication under the Part:

i.	A determination of when,

A.	a project agreement is substantially completed, or

B.	an agreement between a special purpose entity and a contractor is substantially performed, as provided under subsection (5).

ii.	A determination of whether a milestone in relation to the improvement has been reached, if reaching the milestone requires an amount to be paid.

iii.	Any prescribed matters.

2.	If the parties to a project agreement are the parties to an adjudication and the project agreement specifies an independent certifier, the parties shall, provided that a representative of the independent certifier is listed as an adjudicator in the registry established under clause 13.3 (1) (c), request that the representative conduct the adjudication, in which case subsections 13.9 (2) and (3) do not apply.

4 (1) Subclause 2 (1) (b) (i) of the Act is amended by striking out “$500,000” and substituting “$1,000,000”.

(2) Subclause 2 (1) (b) (ii) of the Act is amended by striking out “$500,000” and substituting “$1,000,000”.

(3) Subsection 2 (2) of the Act is amended by striking out “the remainder of the improvement cannot be completed expeditiously for reasons beyond the control of the contractor or, where”.

(4)  Section 2 of the Act is amended by adding the following subsections:

Adjudication amounts

(2.1)  For the purposes of this Act, if an adjudicator makes a determination under Part II.1 in relation to a contract before the certification or declaration of the substantial performance of the contract under section 32,

(a)	any amount determined by the adjudicator to be payable by a party to the contract shall be added to the contract price in determining substantial performance; and

(b)	any amount determined by the adjudicator to have been overpaid by a party to the contract shall be deducted from the contract price in determining substantial performance.

Same

(2.2)  Subsection (2.1) ceases to apply if,

(a)	the adjudicator’s determination ceases to be binding on the parties to the adjudication under section 13.15; or

(b)	the determination of the adjudicator is set aside on judicial review.

(5) The French version of subsection 2 (3) of the Act is amended by striking out “services et matériaux” wherever it appears and substituting in each case “services ou matériaux”.

(6) Clause 2 (3) (b) of the Act is amended by striking out “$1,000” and substituting “$5,000”.

(7) Section 2 of the Act is amended by adding the following subsection:

Multiple improvements under a contract

(4) If more than one improvement is to be made under a contract and each of the improvements is to lands that are not contiguous, then, if the contract so provides, each improvement is deemed for the purposes of this section to be under a separate contract.

5 Subsection 3 (2) of the Act is repealed.

6 (1) The French version of section 6 of the Act is amended by striking out “un avis de privilège” and substituting “une revendication de privilège”.

(2)  Section 6 of the Act is repealed and the following substituted:

Minor errors, irregularities

6 (1)  No certificate, declaration or claim for lien is invalidated by reason only of a failure to comply strictly with subsection 32 (2), 33 (1) or 34 (5) unless, in the opinion of the court, a person has been prejudiced as a result, and then only to the extent of the prejudice suffered.

Same

(2)  Minor errors or irregularities to which subsection (1) applies include,

(a)	a minor error or irregularity in,

(i)	the name of an owner, a person for whom services or materials were supplied or a payment certifier,

(ii)	the legal description of a premises, or

(iii)	the address for service; and

(b)	including an owner’s name in the wrong portion of a claim for lien.

7 The Act is amended by adding the following Part:

Part i.1
prompt payment

Definition, “proper invoice”

6.1 In this Part,

“proper invoice” means a written bill or other request for payment for services or materials in respect of an improvement under a contract, if it contains the following information and, subject to subsection 6.3 (2), meets any other requirements that the contract specifies:

1.	The contractor’s name and address.

2.	The date of the proper invoice and the period during which the services or materials were supplied.

3.	Information identifying the authority, whether in the contract or otherwise, under which the services or materials were supplied.

4.	A description, including quantity where appropriate, of the services or materials that were supplied.

5.	The amount payable for the services or materials that were supplied, and the payment terms.

6.	The name, title, telephone number and mailing address of the person to whom payment is to be sent.

7.	Any other information that may be prescribed.

Subject to holdback requirements

6.2  A requirement to pay an amount in accordance with this Part is subject to any requirement to retain a holdback in accordance with Part IV.

Giving of proper invoices

6.3 (1) Proper invoices shall be given to an owner on a monthly basis, unless the contract provides otherwise.

Restriction on conditions

(2) A provision in a contract that makes the giving of a proper invoice conditional on the prior certification of a payment certifier or on the owner’s prior approval is of no force or effect.

Same

(3) For greater certainty, subsection (2) has no application to a provision in a contract that provides for the certification of a payment certifier or the owner’s approval after a proper invoice is given.

Exception

(4)  Subsection (2) does not apply to a provision in a contract that provides for the testing and commissioning of the improvement or of services or materials supplied under the contract.

Revisions

(5)  A proper invoice may be revised by the contractor after the contractor has given it to the owner, if,

(a)	the owner agrees in advance to the revision;

(b)	the date of the proper invoice is not changed; and

(c)	the proper invoice continues to meet the requirements referred to in the definition of “proper invoice” in section 6.1.

Payment deadline, owner to contractor

6.4 (1) Subject to the giving of a notice of non-payment under subsection (2), an owner shall pay the amount payable under a proper invoice no later than 28 days after receiving the proper invoice from the contractor.

Exception, notice of non-payment if dispute

(2) An owner who disputes a proper invoice may refuse to pay all or any portion of the amount payable under the proper invoice within the time specified in subsection (1) if, no later than 14 days after receiving the proper invoice from the contractor, the owner gives to the contractor a notice of non-payment, in the prescribed form and manner, specifying the amount of the proper invoice that is not being paid and detailing all of the reasons for non-payment.

Requirement to pay remaining amount

(3) Subsection (1) continues to apply to any amount payable under the proper invoice that is not the subject of a notice under subsection (2).

Payment deadlines, contractor to subcontractor

Full payment

6.5 (1) Subject to the giving of a notice of non-payment under subsection (6), a contractor who receives full payment of a proper invoice within the time specified in subsection 6.4 (1) shall, no later than seven days after receiving payment, pay each subcontractor who supplied services or materials under a subcontract with the contractor that were included in the proper invoice the amount payable to the subcontractor.

Partial payment, paid amount

(2) Subject to the giving of a notice of non-payment under subsection (6), if the payment received by the contractor from the owner is only for a portion of the amount payable under a proper invoice, the contractor shall, no later than seven days after receiving payment, pay each subcontractor who supplied services or materials under a subcontract with the contractor that were included in the proper invoice from the amount paid by the owner.

Same

(3) For the purposes of subsection (2), if more than one subcontractor is entitled to payment, payment shall be made in accordance with the following rules:

1.	If the amount not paid by the owner is specific to services or materials supplied by a particular subcontractor or subcontractors, the remaining subcontractors shall be paid, with any amount paid by the owner in respect of the subcontractor or subcontractors who are implicated in the dispute payable to them on a rateable basis, as applicable.

2.	In any other case, subcontractors shall be paid on a rateable basis.

Non or partial payment, unpaid amount

(4) Subject to the giving of a notice of non-payment under subsection (5) or (6), if the owner does not pay some or all of a proper invoice within the time specified in subsection 6.4 (1), the contractor shall, no later than 35 days after giving the proper invoice to the owner, pay each subcontractor who supplied services or materials under a subcontract with the contractor that were included in the proper invoice the amount payable to the subcontractor, to the extent that he or she was not paid fully under subsection (2).

Exception, notice of non-payment if owner does not pay

(5) Subsection (4) does not apply in respect of a subcontractor if, no later than the date specified in subsection (7), the contractor gives to the subcontractor, in the prescribed manner,

(a)	a notice of non-payment, in the prescribed form,

(i)	stating that some or all of the amount payable to the subcontractor is not being paid within the time specified in subsection (4) due to non-payment by the owner,

(ii)	specifying the amount not being paid, and

(iii)	providing an undertaking to refer the matter to adjudication under Part II.1 no later than 21 days after giving the notice to the subcontractor; and

(b)	a copy of any notice of non-payment given by the owner under subsection 6.4 (2).

Exception, notice of non-payment if dispute

(6) A contractor who disputes, in whole or in part, the entitlement of a subcontractor to payment of an amount under the subcontract may refuse to pay all or any portion of the amount within the time specified in subsection (1), (2) or (4), as the case may be, if, no later than the date specified in subsection (7), the contractor gives to the subcontractor a notice of non-payment, in the prescribed form and manner, specifying the amount that is not being paid and detailing all of the reasons for non-payment.

Timing of notice

(7) For the purposes of subsections (5) and (6), the contractor must give notice no later than,

(a)	seven days after receiving a notice of non-payment from the owner under subsection 6.4 (2); or

(b)	if no notice was given by the owner, before the expiry of the period referred to in subsection (4).

Payment deadline once payment received from owner

(8) Subsections (1) and (2) apply, with necessary modifications, in respect of any amount that is the subject of a notice under subsection (5), once the amount is paid by the owner.

Payment deadlines, subcontractor to subcontractor

Full payment

6.6 (1) Subject to the giving of a notice of non-payment under subsection (7), a subcontractor who receives full payment from a contractor in respect of a proper invoice within the time specified in subsection 6.5 (1) shall, no later than seven days after receiving payment, pay each subcontractor who supplied services or materials under a subcontract between them that were included in the proper invoice the amount payable to the subcontractor.

Partial payment, paid amount

(2) Subject to the giving of a notice of non-payment under subsection (7), if the payment received by the subcontractor from the contractor is only for a portion of the amount payable to the subcontractor in respect of a proper invoice, the subcontractor shall, no later than seven days after receiving payment, pay each subcontractor who supplied services or materials under a subcontract between them that were included in the proper invoice from the amount paid by the contractor.

Same

(3) For the purposes of subsection (2), if more than one subcontractor is entitled to payment, payment shall be made in accordance with the following rules:

1.	If the amount not paid by the contractor is specific to services or materials supplied by a particular subcontractor or subcontractors, the remaining subcontractors shall be paid, with any amount paid by the contractor in respect of the subcontractor or subcontractors who are implicated in the dispute payable to them on a rateable basis, as applicable.

2.	In any other case, subcontractors shall be paid on a rateable basis.

Non or partial payment, unpaid amount

(4) Subject to the giving of a notice of non-payment under subsection (6) or (7), if the contractor does not pay some or all of the amount payable to a subcontractor in respect of a proper invoice within the time specified in section 6.5, the subcontractor shall, no later than the date specified in subsection (5), pay each subcontractor who supplied services or materials under a subcontract between them that were included in the proper invoice the amount payable to the subcontractor, to the extent that he or she was not paid fully under subsection (2).

Same, payment deadline

(5) For the purposes of subsection (4), the subcontractor shall pay the amounts no later than,

(a)	seven days after the subcontractor receives payment from the contractor; or

(b)	if no payment is made by the contractor to the subcontractor, 42 days after the proper invoice was given to the owner.

Exception, notice of non-payment if contractor does not pay

(6) Subsection (4) does not apply in respect of a subcontractor if, no later than the date specified in subsection (8), the subcontractor required to pay under subsection (4) gives to the other subcontractor, in the prescribed manner,

(a)	a notice of non-payment, in the prescribed form,

(i)	stating that some or all of the amount payable to the subcontractor is not being paid within the time specified in subsection (4) due to non-payment by the contractor,

(ii)	specifying the amount not being paid, and

(iii)	unless the failure of the contractor to pay is as a result of non-payment by the owner, providing an undertaking to refer the matter to adjudication under Part II.1 no later than 21 days after giving the notice to the subcontractor; and

(b)	a copy of any notices of non-payment received by the subcontractor in relation to the proper invoice.

Exception, notice of non-payment if dispute

(7) A subcontractor who disputes, in whole or in part, the entitlement of another subcontractor to payment of an amount under the subcontract may refuse to pay all or any portion of the amount within the time specified in subsection (1), (2) or (4), as the case may be, if, no later than the date specified in subsection (8), the subcontractor gives to the other subcontractor a notice of non-payment, in the prescribed form and manner, specifying the amount that is not being paid and detailing all of the reasons for non-payment.

Timing of notice

(8) For the purposes of subsections (6) and (7), the subcontractor must give notice no later than,

(a)	seven days after receiving a notice of non-payment from the contractor under subsection 6.5 (5) or (6); or

(b)	if no notice was given by the contractor, before the expiry of the period referred to in clause (5) (b).

Payment deadline once payment received from contractor

(9) Subsections (1) and (2) apply, with necessary modifications, in respect of any amount that is the subject of a notice under subsection (6), once the amount is paid by the contractor.

Date proper invoice was given

(10) On the request of a subcontractor who is required to make payments in accordance with this section, a contractor shall, as soon as possible, provide to the subcontractor confirmation of the date on which the contractor gave a proper invoice to the owner.

Further application

(11) This section applies, with necessary modifications, in respect of a subcontractor who is entitled to payment in accordance with this section and any amounts payable by that subcontractor to any other subcontractor under a subcontract in respect of the improvement.

Reasons for non-payment

6.7  Reasons for non-payment in accordance with this Part may include the retention of amounts under section 12 (set-off by trustee) or under subsection 17 (3) (lien set-off).

No effect on wages

6.8 Nothing in this Part in any way reduces, derogates from or alters the obligations of a contractor or subcontractor to pay wages as provided for by statute, contract or collective bargaining agreement.

Interest on late payments

6.9  Interest begins to accrue on an amount that is not paid when it is due to be paid under this Part, at the prejudgment interest rate determined under subsection 127 (2) of the Courts of Justice Act or, if the contract or subcontract specifies a different interest rate for the purpose, the greater of the prejudgment interest rate and the interest rate specified in the contract or subcontract.

8 The Act is amended by adding the following section:

Contractor’s, subcontractor’s duties re trust funds

8.1 (1) Every person who is a trustee under section 8 shall comply with the following requirements respecting the trust funds of which he or she is trustee:

1.	The trust funds shall be deposited into a bank account in the trustee’s name. If there is more than one trustee of the trust funds, the funds shall be deposited into a bank account in all of the trustees’ names.

2.	The trustee shall maintain written records respecting the trust funds, detailing the amounts that are received into and paid out of the funds, any transfers made for the purposes of the trust, and any other prescribed information.

3.	If the person is a trustee of more than one trust under section 8, the trust funds may be deposited together into a single bank account, as long as the trustee maintains the records required under paragraph 2 separately in respect of each trust.

Multiple trust funds in single account

(2) Trust funds from separate trusts that are deposited together into a single bank account in accordance with subsection (1) are deemed to be traceable, and the depositing of trust funds in accordance with that subsection does not constitute a breach of trust.

9 The French version of subsection 9 (1) of the Act is amended by striking out “intérêt dans un local” in the portion before clause (a) and substituting “intérêt sur des lieux”.

10 (1) The French version of section 12 of the Act is repealed and the following substituted:

Compensation par le fiduciaire

12 Sous réserve de la partie IV, un fiduciaire peut, sans manquer à ses obligations en cette qualité, retenir sur des fonds en fiducie un montant qui, eu égard à la relation qui existe entre le fiduciaire et la personne envers laquelle il est tenu aux termes d’un contrat ou d’un contrat de sous-traitance relatif aux améliorations, est égal au solde en sa faveur des dettes, réclamations ou dommages-intérêts non réglés, que ceux-ci se rapportent ou non aux améliorations.

(2)  Section 12 of the Act is amended by striking out “all outstanding debts, claims or damages, whether or not related to the improvement” at the end and substituting “all outstanding debts, claims or damages related to the improvement or, if the contractor or subcontractor, as the case may be, becomes insolvent, all outstanding debts, claims or damages whether or not related to the improvement”.

11 (1) The Act is amended by adding the following Part:

part ii.1
construction dispute interim adjudication

Definitions

13.1 In this Part,

“adjudication” means construction dispute interim adjudication under this Part with respect to a matter referred to in section 13.5; (“arbitrage intérimaire”)

“adjudicator” means a person who is qualified by the Authority as an adjudicator; (“arbitre intérimaire”)

“Authority” means the Authorized Nominating Authority designated under section 13.2; (“Autorité”)

“notice of adjudication” means a notice that meets the requirements of section 13.7. (“avis d’arbitrage intérimaire”)

Authorized Nominating Authority

13.2 (1)  The Minister responsible for the administration of this Act may designate an entity to act as Authorized Nominating Authority for the purposes of this Part.

Criteria

(2) An entity may not be designated under subsection (1), or act as Authorized Nominating Authority, unless it meets the prescribed criteria, if any.

Duties and powers of Authority

Duties

13.3 (1) The Authority shall,

(a)	develop and oversee programs for the training of persons as adjudicators;

(b)	qualify persons who meet the prescribed requirements as adjudicators;

(c)	establish and maintain a publicly available registry of adjudicators;

(d)	appoint adjudicators for the purposes of subsection 13.9 (5); and

(e)	perform any other duties of the Authority set out in this Part or that may be prescribed for the purposes of this Part.

Powers

(2) The Authority may,

(a)	subject to the regulations, set fees for the training and qualification of persons as adjudicators and for the appointment of adjudicators, and require their payment; and

(b)	exercise any other power of the Authority set out in this Part or that may be prescribed for the purposes of this Part.

Minister as interim Authority

13.4 (1) The Minister responsible for the administration of this Act may act as Authorized Nominating Authority in accordance with subsection (2) on an interim basis, for any period during which an entity is not designated under section 13.2.

Same

(2) If the Minister responsible for the administration of this Act acts as Authorized Nominating Authority, the Minister,

(a)	shall, subject to subsection (3), perform the duties of the Authority, other than the duty set out in clause 13.3 (1) (a); and

(b)	may exercise the powers of the Authority, other than the power set out in clause 13.3 (2) (a).

Same

(3) A duty of the Authority that is set out in the regulations for the purposes of clause 13.3 (1) (e) must only be performed by the Minister if the regulations prescribed for the purposes of this section so provide.

Availability of adjudication

Contract

13.5 (1) Subject to subsection (3), a party to a contract may refer to adjudication a dispute with the other party to the contract respecting any of the following matters:

1.	The valuation of services or materials provided under the contract.

2.	Payment under the contract, including in respect of a change order, whether approved or not, or a proposed change order.

3.	Disputes that are the subject of a notice of non-payment under Part I.1.

4.	Amounts retained under section 12 (set-off by trustee) or under subsection 17 (3) (lien set-off).

5.	Payment of a holdback under section 26.1 or 26.2.

6.	Non-payment of holdback under section 27.1.

7.	Any other matter that the parties to the adjudication agree to, or that may be prescribed.

Subcontract

(2) Subject to subsection (3), a party to a subcontract may refer to adjudication a dispute with the other party to the subcontract respecting any of the matters referred to in subsection (1), with necessary modifications.

Expiry of adjudication period

(3) An adjudication may not be commenced if the notice of adjudication is given after the date the contract or subcontract is completed, unless the parties to the adjudication agree otherwise.

Multiple matters

(4) An adjudication may only address a single matter, unless the parties to the adjudication and the adjudicator agree otherwise.

Application despite other proceeding

(5) A party may refer a matter to adjudication under this Part even if the matter is the subject of a court action or of an arbitration under the Arbitration Act, 1991, unless the action or arbitration has been finally determined.

Adjudication procedures

13.6 (1) Subject to subsection (2), an adjudication is subject to the adjudication procedures set out in the contract or subcontract, if they comply with the requirements of this Part.

Same

(2) If the contract or subcontract does not address adjudication procedures, or if the adjudication procedures set out in the contract or subcontract do not comply with the requirements of this Part, the adjudication is subject to the adjudication procedures set out in this Part and in the regulations.

Notice of adjudication

13.7 (1) A party to a contract or subcontract who wishes to refer a dispute to adjudication shall give to the other party a written notice of adjudication that includes,

(a)	the names and addresses of the parties;

(b)	the nature and a brief description of the dispute, including details respecting how and when it arose;

(c)	the nature of the redress sought; and

(d)	the name of a proposed adjudicator to conduct the adjudication.

Copies

(2) If the regulations so provide, a party who gives notice under subsection (1) shall give a copy of the notice, in the prescribed manner, to the prescribed persons or entities.

Consolidated adjudications

13.8  (1)  If the same matter or related matters in respect of an improvement are the subject of disputes to be adjudicated in separate adjudications under subsections 13.5 (1) and (2), the parties to each of the adjudications may agree to the adjudication of the disputes together by a single adjudicator as a consolidated adjudication.

May be required by contractor

(2)  If the same matter or related matters in respect of an improvement are the subject of disputes to be adjudicated in separate adjudications under subsections 13.5 (1) and (2) but the parties to each of the adjudications do not agree to consolidated adjudication, the contractor may, in accordance with the regulations, nevertheless require the consolidation of the adjudications.

Application

(3)  This Part applies with the following and any other necessary modifications to a consolidated adjudication:

1.	Subsection 13.10 (3) does not apply, and the adjudicator may determine how the adjudication fee is to be apportioned between the parties.

2.	The reference in subsection 13.12 (3) to either or both parties to an adjudication shall be read as a reference to any or all of the parties to the consolidated adjudication.

3.	The references in section 13.17 to the other party to the adjudication shall be read as a reference to any party to the consolidated adjudication.

Multiple matters permitted

(4)  This section applies despite subsection 13.5 (4).

Adjudicator

13.9 (1) An adjudication may only be conducted by an adjudicator listed in the registry established under clause 13.3 (1) (c).

Selection of adjudicator

(2) The parties to the adjudication may agree to an adjudicator, or may request that the Authority appoint an adjudicator.

Contract, subcontract may not name adjudicator

(3) A provision in a contract or subcontract that purports to name a person to act as an adjudicator in the event of an adjudication is of no force or effect.

Requirement to request appointment

(4) If an adjudicator does not consent to conduct the adjudication within four days after the notice of adjudication is given, the party who gave the notice shall request that the Authority appoint an adjudicator.

Appointment

(5) The Authority shall appoint an adjudicator, subject to his or her prior consent, to conduct an adjudication no later than seven days after receiving a request for the appointment.

No requirement to act

(6) Nothing in this Part or the regulations shall be read as requiring an adjudicator to agree to conduct an adjudication or to accept an appointment by the Authority to conduct an adjudication.

Adjudicator fee

13.10 (1) An adjudicator shall be paid a fee for conducting the adjudication, which shall be determined in accordance with subsection (2) before the adjudication commences.

Fee amount

(2) The fee payable to an adjudicator is,

(a)	the fee agreed to by the parties to the adjudication and the adjudicator; or

(b)	if the parties and the adjudicator do not agree to a fee amount, the amount determined by the Authority, in accordance with the regulations, if any, on the adjudicator’s request.

Equal apportionment

(3) The parties to the adjudication shall split payment of the adjudication fee equally, subject to a different determination under section 13.17.

Documents for adjudication

13.11 No later than five days after an adjudicator agrees or is appointed to conduct the adjudication, the party who gave the notice of adjudication shall give to the adjudicator a copy of the notice, together with,

(a)	a copy of the contract or subcontract; and

(b)	any documents the party intends to rely on during the adjudication.

Conduct of adjudication

Powers of adjudicator

13.12 (1) In conducting an adjudication, an adjudicator may exercise the following powers and any other power of an adjudicator that may be specified in the contract or subcontract:

1.	Issuing directions respecting the conduct of the adjudication.

2.	Taking the initiative in ascertaining the relevant facts and law.

3.	Drawing inferences based on the conduct of the parties to adjudication.

4.	Subject to subsection (2), conducting an on-site inspection of the improvement that is the subject of the contract or subcontract.

5.	Obtaining the assistance of a merchant, accountant, actuary, building contractor, architect, engineer or other person in such a way as the adjudicator considers fit, as is reasonably necessary to enable him or her to determine better any matter of fact in question.

6.	Making a determination in the adjudication.

7.	Any other power that may be prescribed.

On-site inspection

(2) The exercise of the power to conduct an on-site inspection under paragraph 4 of subsection (1) is subject to the prior consent of,

(a)	the owner of the premises if,

(i)	the premises is a home in which the owner resides, or

(ii)	the owner is not a party to the adjudication; and

(b)	any other person who has the legal authority to exclude others from the premises.

Costs of assistance

(3) If the adjudicator obtains the assistance of a person under paragraph 5 of subsection (1), the adjudicator may fix the remuneration of the person as is reasonable and proportionate to the dispute and direct payment of the remuneration by either or both of the parties to the adjudication.

Conduct

(4) Subject to this section, the adjudicator may conduct the adjudication in the manner he or she determines appropriate in the circumstances.

Impartiality

(5) An adjudicator shall conduct an adjudication in an impartial manner.

Statutory Powers Procedure Act

(6) The Statutory Powers Procedure Act does not apply to adjudications.

Determination

13.13 (1) Subject to subsection (2), an adjudicator shall make a determination of the matter that is the subject of an adjudication no later than 30 days after receiving the documents required by section 13.11.

Extension

(2) The deadline for an adjudicator’s determination may be extended, at any time before its expiry and after the giving of documents to the adjudicator under section 13.11,

(a)	on the adjudicator’s request, with the written consent of the parties to the adjudication, for a period of no more than 14 days; or

(b)	on the written agreement of the parties to the adjudication, subject to the adjudicator’s consent, for the period specified in the agreement.

Notice of extension

(3)  If the party who gave the notice of adjudication also gave a notice of non-payment under Part I.1 in relation to the matter that is the subject of the adjudication, the party shall give notice of an extension under clause (2) (b), specifying the period of the extension, to the person to whom he or she gave the notice of non-payment.

Same

(4)  A person who receives notice of an extension under subsection (3) or under this subsection shall give notice of the extension, specifying the period of the extension, to any person to whom he or she gave notice of non-payment under Part I.1 in relation to the matter that is the subject of the adjudication.

Delayed determination

(5) A determination made by an adjudicator after the date determined under subsection (1) or (2) is of no force or effect.

Written reasons

(6) The adjudicator’s determination shall be in writing and shall include reasons for the determination.

Admissibility

(7)  The determination and reasons of an adjudicator are admissible as evidence in court.

Termination of adjudication

13.14 At any time after the notice of adjudication is given and before the adjudicator makes his or her determination, the parties to the adjudication may agree to terminate the adjudication, on notice to the adjudicator and subject to the payment of the adjudicator’s fee.

Effect of determination

13.15 (1)  The determination of a matter by an adjudicator is binding on the parties to the adjudication until a determination of the matter by a court, a determination of the matter by way of an arbitration conducted under the Arbitration Act, 1991, or a written agreement between the parties respecting the matter.

Authority of court, arbitrator

(2)  Subject to section 13.18, nothing in this Part restricts the authority of a court or of an arbitrator acting under the Arbitration Act, 1991 to consider the merits of a matter determined by an adjudicator.

Costs

13.16 Subject to section 13.17, the parties to an adjudication shall bear their own costs of the adjudication.

Frivolous, vexatious, etc.

13.17 If an adjudicator determines that a party to the adjudication has acted in respect of the improvement in a manner that is frivolous, vexatious, an abuse of process or other than in good faith, the adjudicator may provide, as part of his or her determination of the matter, that the party be required to pay some or all of the other party’s costs, any part of the fee amount determined under section 13.10 that would otherwise be payable by the other party, or both.

Setting aside on judicial review

Leave required

13.18  (1)  An application for judicial review of a determination of an adjudicator may only be made with leave of the Divisional Court in accordance with this section and the rules of court.

Timing

(2)  A motion for leave to bring an application for judicial review of a determination of an adjudicator shall be filed, with proof of service, in accordance with the rules of court no later than 30 days after the determination is communicated to the parties.

Dismissal without reasons

(3)  A motion for leave to bring an application for judicial review may be dismissed without reasons.

No appeal

(4)  No appeal lies from an order on a motion for leave to bring an application for judicial review.

Setting aside only for specified reasons

(5)  The determination of an adjudicator may only be set aside on an application for judicial review if the applicant establishes one or more of the following grounds:

1.	The applicant participated in the adjudication while under a legal incapacity.

2.	The contract or subcontract is invalid or has ceased to exist.

3.	The determination was of a matter that may not be the subject of adjudication under this Part, or of a matter entirely unrelated to the subject of the adjudication.

4.	The adjudication was conducted by someone other than an adjudicator.

5.	The procedures followed in the adjudication did not comply with the procedures to which the adjudication was subject under this Part, and the failure to comply prejudiced the applicant’s right to a fair adjudication.

6.	There is a reasonable apprehension of bias on the part of the adjudicator.

7.	The determination was made as a result of fraud.

Amounts paid

(6)  If the Divisional Court sets aside the decision of an adjudicator, the Court may require that any or all amounts paid in compliance with the determination be returned.

No stay

(7)  An application for judicial review of a decision of an adjudicator does not operate as a stay of the operation of the determination unless the Divisional Court orders otherwise.

Amounts payable

Subject to holdback

13.19 (1)  A requirement to pay an amount in accordance with this section is subject to any requirement to retain a holdback in accordance with Part IV.

Enforcement of amounts payable

(2) A party who is required under the determination of an adjudicator to pay an amount to another person shall pay the amount no later than 10 days after the determination has been communicated to the parties to the adjudication.

Interest on late payments

(3)  Interest begins to accrue on an amount that is not paid when it is due to be paid under this Part, at the prejudgment interest rate determined under subsection 127 (2) of the Courts of Justice Act or, if the contract or subcontract specifies a different interest rate for the purpose, the greater of the prejudgment interest rate and the interest rate specified in the contract or subcontract.

No interest on interest

(4) Subsection (3) does not apply in respect of any amount payable under section 6.9.

Suspension of work

(5) If an amount payable to a contractor or subcontractor under a determination is not paid by the party when it is due under this section, the contractor or subcontractor may suspend further work under the contract or subcontract until the party pays the following amounts:

1.	The amount required to be paid under the determination.

2.	Any interest accrued on that amount under subsection (3).

3.	Any reasonable costs incurred by the contractor or subcontractor as a result of the suspension of work.

Same, costs of resumption

(6) A contractor or subcontractor who suspends work under subsection (5) is entitled to payment, by the party, of any reasonable costs incurred by him or her as a result of the resumption of work following the payment of the amounts referred to in that subsection.

Enforcement by court

13.20  (1)  A party to an adjudication may, no later than the date referred to in subsection (2), file a certified copy of the determination of an adjudicator with the court and, on filing, the determination is enforceable as if it were an order of the court.

Deadline

(2)  The filing of a determination under subsection (1) may not be made after the later of,

(a)	the second anniversary of the communication of the determination to the parties; and

(b)	if a party makes a motion under section 13.18 for leave to bring an application for judicial review of a determination of an adjudicator, the second anniversary of the dismissal of the motion or, if the motion was not dismissed, the final determination of the application, if it did not result in the adjudicator’s determination being set aside.

Notice of filing

(3)  A party shall, no later than 10 days after filing a determination under subsection (1), notify the other party of the filing.

Effect on requirement to make payments

(4)  If a determination requiring that an amount be paid to a contractor or subcontractor is filed under subsection (1), any related requirement of the contractor or subcontractor, as the case may be, to make payment to a subcontractor is deferred pending the outcome of the enforcement.

Immunity

13.21 No action or other proceeding shall be commenced against an adjudicator or his or her employees for any act done in good faith in the execution or intended execution of any duty or power under this Part or the regulations, or for any alleged neglect or default in the execution in good faith of that duty or power.

Testimonial immunity

13.22 An adjudicator shall not be compelled to give evidence in any action or other proceeding in respect of a matter that was the subject of an adjudication that he or she conducted.

(2) Part II.1 of the Act, as enacted by subsection (1), is amended by adding the following section:

Application of Part to surety bonds (Part XI.1)

13.23 If the regulations so provide, this Part applies, with such modifications as the regulations specify, to disputes in respect of such surety bonds to which Part XI.1 applies as are specified by the regulations.

12 (1) The French version of subsection 14 (1) of the Act is amended by striking out “le local ainsi amélioré” and substituting “les lieux ainsi améliorés”.

(2) Section 14 of the Act is amended by adding the following subsection:

Architects

(3) For greater certainty, subsection (1) applies to services or materials supplied by an architect as defined in the Architects Act and any employees of the architect.

13 (1) The French version of subsection 16 (1) of the Act is amended by striking out “dans un local” at the end and substituting “sur des lieux”.

(2) The French version of subsection 16 (2) of the Act is amended by striking out “un local dans lequel” and substituting “des lieux sur lesquels” and by striking out “dans ce local” and substituting “sur ces lieux”.

(3) The French version of subsection 16 (3) of the Act is repealed and the following substituted:

Cas où le privilège ne grève pas les lieux

(3) Lorsque la Couronne est propriétaire de lieux au sens de la présente loi ou que ceux-ci consistent, selon le cas:

a)	en une rue ou une voie publique qui est la propriété d’une municipalité;

b)	en une emprise ferroviaire,

le privilège ne grève pas les lieux mais constitue une sûreté prévue à l’article 21 et les dispositions de la présente loi prennent effet sans qu’il soit nécessaire d’enregistrer de revendication de privilège à l’égard des lieux.

(4) Section 16 of the Act is repealed and the following substituted:

Crown, municipal interest in premises

16 (1) A lien does not attach to the interest in a premises of,

(a)	the Crown; or

(b)	a municipality.

Interest of other person

(2) Where an improvement is made to a premises in which the Crown or a municipality has an interest but the Crown or municipality is not an owner of the premises, the lien may attach to the interest of any other person in the premises.

Where lien does not attach to premises

(3) A lien does not attach to a premises, but constitutes a charge under section 21, if,

(a)	the owner of the premises is the Crown or a municipality; or

(b)	the premises is a railway right-of-way.

14 (1) The French version of subsection 17 (3) of the Act is repealed and the following substituted:

Compensation

(3) Sous réserve de la partie IV, afin de fixer le montant visé par le privilège aux termes du paragraphe (1) ou (2), il peut être tenu compte du montant qui, eu égard à la relation qui existe entre le responsable du paiement et la personne envers laquelle il est tenu, est égal au solde en faveur du responsable du paiement des dettes, réclamations et dommages-intérêts non réglés, que ceux-ci se rapportent ou non aux améliorations.

(2)  Subsection 17 (3) of the Act is amended by striking out “all outstanding debts, claims or damages, whether or not related to the improvement” at the end and substituting “all outstanding debts, claims or damages related to the improvement or, if the contractor or subcontractor, as the case may be, becomes insolvent, all outstanding debts, claims or damages whether or not related to the improvement”.

(3) The French version of subsection 17 (4) of the Act is amended by striking out “du privilège mentionné à l’avis, en regard” and substituting “d’une revendication de privilège à l’égard”.

(4) Subsection 17 (4) of the Act is amended by striking out “in respect of a public street or highway” at the end.

15 The French version of section 18 of the Act is amended by striking out “dans le local” and substituting “sur les lieux”.

16 (1) Subsection 19 (1) of the Act is repealed and the following substituted:

Leasehold interest

(1) If the interest of the owner to which a lien attaches is leasehold, and if payment for all or part of the improvement is accounted for under the terms of the lease or any renewal of it, or under any agreement to which the landlord is a party that is connected to the lease, the landlord’s interest is also subject to the lien, to the extent of 10 percent of the amount of such payment.

(2) The French version of subsection 19 (3) of the Act is amended by striking out “qu’un avis de privilège est enregistré” and substituting “qu’une revendication de privilège est enregistrée” and by striking out “un avis de privilège” and substituting “une revendication de privilège”.

(3) Section 19 of the Act is amended by adding the following subsection:

Landlord as owner

(5) Nothing in this section prevents a determination in respect of a premises that the landlord is instead its owner, if he or she meets the criteria set out in the definition of “owner” in subsection 1 (1).

17 (1) Subsection 22 (1) of the Act is amended by striking out “have expired as provided in Part V, or have been satisfied, discharged or provided for under section 44 (payment into court)” at the end and substituting “have expired or been satisfied, discharged or otherwise provided for under this Act”.

(2) Subsection 22 (2) of the Act is amended by striking out “have expired as provided in Part V, or have been satisfied, discharged or provided for under section 44” at the end and substituting “have expired or been satisfied, discharged or otherwise provided for under this Act”.

(3) Section 22 of the Act is amended by adding the following subsection:

Permissible forms of holdback

(4) Some or all of any holdbacks may, instead of being retained in the form of funds, be retained in one or more of the following forms:

1.	A letter of credit in the prescribed form.

2.	A demand-worded holdback repayment bond in the prescribed form.

3.	Any other form that may be prescribed.

18 Subsection 23 (5) of the Act is repealed.

19 (1) The French version of subsection 24 (1) of the Act is amended by striking out “en toute sûreté” and substituting “sans risque”.

(2) The French version of subsection 24 (2) of the Act is amended by striking out “, en toute sûreté” and substituting “sans risque”.

(3) Subsection 24 (2) of the Act is amended by striking out “services and materials” and substituting “services or materials”.

20 (1) The French version of section 25 of the Act is amended by striking out “, en toute sûreté” and substituting “sans risque”.

(2) Section 25 of the Act is amended by striking out “have expired as provided in Part V, or have been satisfied, discharged or provided for under section 44 (payment into court)” at the end and substituting “have expired or been satisfied, discharged or otherwise provided for under this Act”.

21 (1) The French version of section 26 of the Act is amended by striking out “en toute sûreté” and substituting “sans risque”.

(2) Section 26 of the Act is amended by adding “Subject to section 27.1” at the beginning.

(3) Section 26 of the Act is amended by striking out “may, without jeopardy” and substituting “shall”.

(4) Section 26 of the Act is amended by striking out “have expired as provided in Part V, or have been satisfied, discharged or provided for under section 44” at the end and substituting “have expired or been satisfied, discharged or otherwise provided for under this Act”.

22 The Act is amended by adding the following sections:

Payment of holdback on annual basis

26.1 (1) If the conditions in subsection (2) are met, a payer may make payment of the accrued holdback he or she is required to retain under subsection 22 (1) on an annual basis, in relation to the services or materials supplied during the applicable annual period.

Conditions

(2) Subsection (1) applies if,

(a)	the contract provides for a completion schedule that is longer than one year;

(b)	the contract provides for the payment of accrued holdback on an annual basis;

(c)	the contract price at the time the contract is entered into exceeds the prescribed amount; and

(d)	as of the applicable payment date,

(i)	there are no preserved or perfected liens in respect of the contract, or

(ii)	all liens in respect of the contract have been satisfied, discharged or otherwise provided for under this Act.

Payment of holdback on phased basis

26.2 (1) If the conditions in subsection (2) are met, a payer may make payment of the accrued holdback he or she is required to retain under subsection 22 (1) on the completion of phases of an improvement, in relation to the services or materials supplied during each phase.

Conditions

(2) Subsection (1) applies if,

(a)	the contract provides for the payment of accrued holdback on a phased basis and identifies each phase;

(b)	the contract price at the time the contract is entered into exceeds the prescribed amount; and

(c)	as of the applicable payment date,

(i)	there are no preserved or perfected liens in respect of the contract, or

(ii)	all liens in respect of the contract have been satisfied, discharged or otherwise provided for under this Act.

Payment on completion of design phase

(3) If a contract provides for payment of accrued holdback on a phased basis but only with respect to a specified design phase, clause (2) (b) does not apply.

23 (1) The French version of section 27 of the Act is amended by striking out “en toute sûreté” and substituting “sans risque”.

(2) Section 27 of the Act is amended by adding “Subject to section 27.1” at the beginning.

(3) Section 27 of the Act is amended by striking out “may, without jeopardy” and substituting “shall”.

(4) Section 27 of the Act is amended by striking out “have expired as provided in Part V, or have been satisfied, discharged or provided for under section 44” at the end and substituting “have expired or been satisfied, discharged or otherwise provided for under this Act”.

24 (1)  The Act is amended by adding the following section:

Non-payment of holdback

27.1 An owner may refuse to pay some or all of the amount the owner is required to pay to a contractor under section 26 or 27, as the case may be, if,

(a)	no later than 40 days after publication of the applicable certification or declaration of substantial performance under section 32, the owner publishes, in the manner set out in the regulations, a notice in the prescribed form, specifying the amount of the holdback that the owner refuses to pay; and

(b)	the owner notifies, in accordance with the regulations if any, the contractor of the publication of the notice.

(2)  Section 27.1 of the Act, as enacted by subsection (1), is amended by adding the following subsections:

Adjudication

(2)  A contractor may refuse to pay some or all of the amount the contractor is required to pay to a subcontractor under section 26 or 27, as the case may be, if,

(a)	the owner refuses to pay some or all of the amount the owner is required to pay to the contractor under that section;

(b)	the contractor refers the matter to adjudication under Part II.1; and

(c)	the contractor notifies, in accordance with the regulations if any, every subcontractor to whom the contractor is required to pay the amount that the amount is not being paid and that the matter is being referred to adjudication.

Same

(3)  A subcontractor may refuse to pay some or all of the amount the subcontractor is required to pay to another subcontractor under section 26 or 27, as the case may be, if,

(a)	the contractor refuses to pay some or all of the amount the contractor is required to pay to the subcontractor under that section;

(b)	the subcontractor refers the matter to adjudication under Part II.1; and

(c)	the subcontractor notifies, in accordance with the regulations if any, every subcontractor to whom the subcontractor is required to pay the amount that the amount is not being paid and that the matter is being referred to adjudication.

Same

(4)  Subsection (3) applies, with necessary modifications, with respect to a subcontractor who receives notice under that subsection.

25 Section 30 of the Act is amended by striking out “have expired as provided in Part V, or have been satisfied, discharged or provided for under section 44 (payment into court)” at the end and substituting “have expired or been satisfied, discharged or otherwise provided for under this Act”.

26 (1) Clause 31 (2) (a) of the Act is amended by striking out “forty-five” in the portion before subclause (i) and substituting “60”.

(2) Subclause 31 (2) (a) (ii) of the Act is amended by striking out “completed or abandoned” and substituting “completed, abandoned or terminated”.

(3) Clause 31 (2) (b) of the Act is amended by striking out “forty-five” in the portion before subclause (i) and substituting “60”.

(4) The French version of subclause 31 (2) (b) (i) of the Act is amended by striking out “date de l’achèvement” and substituting “date d’achèvement”.

(5) Subclause 31 (2) (b) (ii) of the Act is amended by adding “or terminated” at the end.

(6) Section 31 of the Act is amended by adding the following subsection:

Workers’ trust fund lien

(2.1) Subject to subsection (4), the lien of the trustee of a workers’ trust fund on behalf of a worker or workers,

(a)	for services or materials supplied to an improvement on or before the date certified or declared to be the date of the substantial performance of the contract, expires at the conclusion of the 60-day period next following the occurrence of the earliest of,

(i)	the date on which a copy of the certificate or declaration of the substantial performance of the contract is published, as provided in section 32,

(ii)	the date on which the final worker who is a beneficiary of the workers’ trust fund last supplies services or materials to the improvement,

(iii)	the date the contract is completed, abandoned or terminated, and

(iv)	the date a subcontract is certified to be completed under section 33, where the services or materials were supplied under or in respect of that subcontract; and

(b)	for services or materials supplied to the improvement where there is no certification or declaration of the substantial performance of the contract, or for services or materials supplied to the improvement after the date certified or declared to be the date of the substantial performance of the contract, expires at the conclusion of the 60-day period next following the occurrence of the earlier of,

(i)	the date on which the final worker who is a beneficiary of the workers’ trust fund last supplied services or materials to the improvement,

(ii)	the date the contract is completed, abandoned or terminated, and

(iii)	the date a subcontract is certified to be completed under section 33, where the services or materials were supplied under or in respect of that subcontract.

(7) Clause 31 (3) (a) of the Act is amended by striking out “forty-five” in the portion before subclause (i) and substituting “60”.

(8) Clause 31 (3) (a) of the Act is amended by striking out “and” at the end of subclauses (i) and (ii) and by adding the following subclause:

(ii.1)	the date the contract is completed, abandoned or terminated, and

(9) Clause 31 (3) (b) of the Act is amended by striking out “forty-five” in the portion before subclause (i) and substituting “60”.

(10) Clause 31 (3) (b) of the Act is amended by striking out “and” at the end of subclause (i) and by adding the following subclause:

(i.1)	the date the contract is completed, abandoned or terminated, and

(11) Section 31 of the Act is amended by adding the following subsections:

Notice of termination

(6) If a contract is terminated, either the owner or the contractor or other person whose lien is subject to expiry shall publish, in the manner set out in the regulations, a notice of the termination in the prescribed form and, for the purposes of this section, the date on which the contract is terminated is the termination date specified in the notice for the contract.

Validity of termination

(7) Subsection (6) does not prevent a person from contesting the validity of a termination.

27 (1) Paragraphs 5 and 9 of subsection 32 (1) of the Act are amended by striking out “once in a construction trade newspaper” wherever it appears and substituting in each case “in the manner set out in the regulations”.

(2) Clauses 32 (2) (e) and (f) of the Act are repealed and the following substituted:

(e)	a legal description of the premises, including all property identifier numbers and addresses for the premises; and

(f)	if the lien does not attach to the premises, the name and address of the person or body to whom a copy of the claim for lien must be given under section 34.

(3) Subsection 32 (5) of the Act is repealed.

28 Subsection 33.1 (2) of the Act is amended by striking out “in a construction trade newspaper at least five and not more than 15 days, excluding Saturdays and holidays, before the description is submitted for approval under subsection 9 (3) of the Condominium Act, 1998” at the end and substituting “in the manner set out in the regulations.”

29 (1) The French version of subsection 34 (2) of the Act is amended by striking out “Si l’avis de privilège porte sur une rue ou une voie publique qui est la propriété d’une municipalité, une copie de cet avis” at the beginning and substituting “Si la revendication de privilège porte sur une rue ou une voie publique qui est la propriété d’une municipalité, une copie de cette revendication”.

(2) Subsection 34 (2) of the Act is repealed.

(3) Subsection 34 (3) of the Act is amended by striking out “office prescribed by regulation” and substituting “prescribed office”.

(4) Section 34 of the Act is amended by adding the following subsection:

Premises owned by municipality

(3.1) Where the owner of the premises is a municipality, the copy of the claim for lien shall be given to the clerk of the municipality.

(5) The French version of subsection 34 (4) of the Act is amended by striking out “Si le local consiste en un droit de passage d’un chemin de fer” at the beginning and substituting “Si les lieux consistent en une emprise ferroviaire”.

(6) Clause 34 (5) (a) of the Act is repealed and the following substituted:

(a)	the name and address for service of the person claiming the lien or, in the case of a claim on behalf of a worker by a workers’ trust fund, the name and address of the trustee;

(a.1)	the name and address of the owner of the premises and of the person for whom the services or materials were supplied;

(a.2)	the time within which the services or materials were supplied;

(7) The French version of subclause 34 (5) (e) (ii) of the Act is amended by striking out “du local, si le privilège ne grève pas celui-ci” at the end and substituting “des lieux, si le privilège ne grève pas ceux-ci”.

(8) The French version of subsection 34 (7) of the Act is amended by striking out “L’avis de privilège” and substituting “La revendication”.

(9) The French version of subsection 34 (8) of the Act is repealed and the following substituted:

Jonction des parties

(8) Plusieurs titulaires de privilège sur les mêmes lieux peuvent être réunis dans une seule revendication de privilège.

(10) Section 34 of the Act is amended by adding the following subsection:

Notice of preservation of lien re common elements of condominium

(9) A person who preserves a lien under this section that relates, in whole or in part, to an improvement to the common elements of a corporation under the Condominium Act, 1998 shall give notice of the lien’s preservation, in the prescribed form, to the corporation and to each person who is,

(a)	in the case of a corporation that is not a common elements condominium corporation, as defined in that Act, an owner of a unit in the corporation; and

(b)	in the case of a common elements condominium corporation, an owner of a parcel of land mentioned in subsection 139 (1) of that Act to which a common interest is attached and which is described in the declaration of the corporation.

(11)  Section 34 of the Act is amended by adding the following subsection:

Adjudication and expiry

(10)  If the matter that is the subject of a lien that has not expired is also a matter that is the subject of an adjudication under Part II.1, the lien is deemed, for the purposes of this section only, to have expired on the later of the date on which the lien would expire under section 31 and the conclusion of the 45-day period next following the receipt by the adjudicator of documents under section 13.11.

30 (1) The French version of section 35 of the Act is amended by striking out “un avis de privilège” in the portion before clause (a) and substituting “une revendication de privilège”.

(2) Section 35 of the Act is repealed and the following substituted:

Exaggerated, false claims

Liability

35 (1) In addition to any other ground on which the person may be liable, any person who preserves a claim for lien or who gives written notice of a lien in the following circumstances is liable to any person who suffers damages as a result:

1.	The person knows or ought to know that the amount of the lien has been wilfully exaggerated.

2.	The person knows or ought to know that he or she does not have a lien.

Reduction of lien amount

(2) In the circumstances described in paragraph 1 of subsection (1), the court may, on motion, order that the lien amount be reduced by the exaggerated portion, as determined in accordance with section 17, if it finds that the person has acted in good faith.

31 (1) Subsection 36 (2) of the Act is amended by striking out “forty-five” and substituting “90”.

(2) The French version of subsection 36 (4) of the Act is amended by striking out “en regard” wherever it appears and substituting in each case “à l’égard”.

(3) Paragraph 3 of subsection 36 (4) of the Act is amended by striking out “A sheltered claim for lien” at the beginning and substituting “A sheltered lien”.

(4) The French version of paragraph 4 of subsection 36 (4) of the Act is amended by striking out “sa demande ou tout fait allégué dans son avis de privilège” at the end and substituting “sa revendication de privilège ou tout fait allégué dans celle-ci”.

32 (1) Paragraph 1 of subsection 39 (1) of the Act is amended by striking out “By the owner or contractor” at the beginning and substituting “By the owner or contractor, other than a landlord described in paragraph 4”.

(2) Subparagraph 1 iii of subsection 39 (1) of the Act is repealed and the following substituted:

iii.	a state of accounts between the owner and the contractor containing the information listed in subsection (4.1),

(3) Paragraph 1 of subsection 39 (1) of the Act is amended by striking out “and” at the end of subparagraph iv, adding “and” at the end of subparagraph v and adding the following subparagraph:

vi.	a statement of whether the contract provides that payment under the contract shall be based on the completion of specified phases or the reaching of other milestones in its completion.

(4) Subparagraph 2 ii of subsection 39 (1) of the Act is repealed and the following substituted:

ii.	a state of accounts between the contractor and a subcontractor, or between a subcontractor and another subcontractor, containing the information listed in subsection (4.1),

(5) The French version of paragraph 3 of subsection 39 (1) of the Act is amended by striking out “intérêt dans le local qui constitue” in the portion before subparagraph i and substituting “intérêt sur les lieux qui constituent”.

(6) Subsection 39 (1) of the Act is amended by adding the following paragraph:

from landlord

4.	By a landlord whose interest in a premises is subject to a lien under subsection 19 (1), with,

i.	the names of the parties to the lease, and

ii.	the amount of the payment referred to in subsection 19 (1).

(7) Paragraph 4 of subsection 39 (1) of the Act, as enacted by subsection (6), is amended by striking out “and” after subparagraph i, adding “and” after subparagraph ii and adding the following subparagraph:

iii.	the state of accounts between the landlord and the tenant containing the information listed in subsection (4.1).

(8)  Subsection 39 (4) of the Act is repealed and the following substituted:

respecting publication of certificate of substantial performance

(4)  A contractor shall, on the written request of a person, provide to the person within a reasonable time after the request is made written confirmation of the date and location of the publication of the copy of the certificate of substantial performance under subsection 32 (1).

(9) Section 39 of the Act is amended by adding the following subsections:

State of accounts

(4.1) A state of accounts under subsection (1) shall contain the following information, as of a specified date:

1.	The price of the services or materials that have been supplied under the contract or subcontract.

2.	The amounts paid under the contract or subcontract.

3.	In the case of a state of accounts under paragraph 4 of subsection (1), which of the amounts paid under the contract or subcontract constitute any part of the payment referred to in subsection 19 (1).

4.	The amount of the applicable holdbacks.

5.	The balance owed under the contract or subcontract.

6.	Any amount retained under section 12 (set-off by trustee) or under subsection 17 (3) (lien set-off).

7.	Any other information that may be prescribed.

Information provided by mortgagee

(4.2) For the purposes of clause (2) (b), if amounts have been advanced under the mortgage for the purposes of financing both the purchase price of the land and the making of the improvement, the statement must show the amount advanced under the mortgage for each of those purposes.

(10) Subsection 39 (5) of the Act is amended by striking out “damages sustained by reason thereof” at the end and substituting “damages suffered as a result”.

33 (1) Clause 41 (1) (a) of the Act is amended by striking out “a release in the prescribed form on the title to the premises and the release shall” and substituting “a discharge of lien in the prescribed form on the title to the premises and the discharge shall”.

(2) Clause 41 (1) (b) of the Act is amended by striking out “a release” and substituting “a discharge of lien”.

(3) Subsection 41 (2) of the Act is amended by striking out “in writing” and substituting “in the prescribed form”.

34 (1) The French version of section 42 of the Act is amended by striking out “le local ainsi libéré” at the end and substituting “les lieux ainsi libérés”.

(2) Section 42 of the Act is amended by striking out “the registration of a release in the prescribed form on the title to the premises released” at the end and substituting “the registration of a discharge of lien in the prescribed form on the title to the applicable premises”.

35 The French version of section 43 of the Act is amended by striking out “dans le local par l’enregistrement à l’égard du titre sur le local” and substituting “sur les lieux par l’enregistrement à l’égard du titre sur les lieux”.

36 (1) Clause 44 (1) (d) of the Act is amended by striking out “$50,000” and substituting “$250,000”.

(2) Section 44 of the Act is amended by adding the following subsections:

Condominium

(2.1) The owner of a condominium unit under the Condominium Act, 1998 may make a motion under clause (1) (a) or subsection (2) regarding a lien respecting an improvement to common elements that include the common interest appurtenant to the owner’s unit, and, for the purpose, the full amount claimed as owing in the claim for lien is deemed to be that portion of the lien amount that is attributable to the owner’s common interest as specified in the applicable declaration registered under that Act.

Common elements condominium corporation

(2.2) An owner of a parcel of land mentioned in subsection 139 (1) of the Condominium Act, 1998 to which a common interest is attached, in the case of a common elements condominium corporation, may make a motion under clause (1) (a) or subsection (2) regarding a lien respecting an improvement to common elements that include the common interest appurtenant to the owner’s parcel of land, and, for the purpose, the full amount claimed as owing in the claim for lien is deemed to be that portion of the lien amount that is attributable to the owner’s common interest as specified in the applicable declaration registered under that Act.

(3) The French version of subsection 44 (3) of the Act is amended by striking out “l’avis de privilège donné” and substituting “la revendication de privilège donnée”.

(4) Section 44 of the Act is amended by adding the following subsection:

Vacating written notice of lien

(3.1) The court shall, on motion, vacate a written notice of a lien if any of the circumstances in subsection (1), (2) or (3) apply.

(5) Section 44 of the Act is amended by adding the following subsection:

Letters of credit

(5.1) A letter of credit containing reference to an international commercial convention is acceptable as security for the purposes of this section, as long as the convention text is written into the terms of the credit and the letter of credit is unconditional and accepted by a bank listed in Schedule I to the Bank Act (Canada) that is operating in Ontario.

(6) Paragraph 1 of subsection 44 (9) of the Act is amended by striking out “the procedures set out in Part VIII” and substituting “the procedures under Part VIII”.

37 (1) Subsection 47 (1) of the Act is repealed and the following substituted:

General powers of the court

Power to discharge

(1) The court may, on motion, order the discharge of a lien,

(a)	on the basis that the claim for the lien is frivolous, vexatious or an abuse of process; or

(b)	on any other proper ground.

Power to vacate, etc.

(1.1) The court may, on motion, make any of the following orders, on any proper ground:

1.	An order that the registration of a claim for lien, a certificate of action or both be vacated.

2.	If written notice of a lien has been given, a declaration that the lien has expired or that the written notice of the lien shall no longer bind the person to whom it was given.

3.	An order dismissing an action.

Conditions

(1.2) An order under subsection (1) or (1.1) may include any terms or conditions that the court considers appropriate in the circumstances.

(2) Subsection 47 (2) of the Act is amended by striking out “subsection (1)” and substituting “paragraph 1 of subsection (1.1)”.

38 The French version of section 49 of the Act is amended by striking out “l’avis de privilège” and substituting “la revendication de privilège” and by striking out “chacun des privilèges qui ont été conservés ou rendus opposables” and substituting “chacune des revendications de privilège qui ont été conservées ou rendues opposables”.

39 (1) The French version of subsection 50 (3) of the Act is amended by striking out “au même local” and substituting “aux mêmes lieux”.

(2) Section 50 of the Act is repealed and the following substituted:

Lien claims and procedures

50 (1) A lien claim is enforceable in an action in the Superior Court of Justice.

Procedures

(2) Except to the extent that they are inconsistent with this Act and the procedures prescribed for the purposes of this Part, the Courts of Justice Act and the rules of court apply to actions under this Part.

Summary procedure

(3) The procedure in an action shall be as far as possible of a summary character, having regard to the amount and nature of the liens in question.

40 (1) Section 51 of the Act is amended by striking out “on a reference by a master, a case management master or a person agreed on by the parties” in the portion before clause (a) and substituting “on a reference under section 58”.

(2) Clause 51 (a) of the Act is amended by striking out “subject to section 56”.

41 Section 52 of the Act is amended by striking out “or for holding a settlement meeting” at the end.

42 (1) The French version of clause 55 (2) (b) of the Act is amended by striking out “en regard” and substituting “à l’égard”.

(2) Sections 53 to 57 of the Act are repealed.

43 (1) Subsection 58 (1) of the Act is amended by striking out “or” at the end of clause (a.1), adding “or” at the end of clause (b), and adding the following clause:

(c)	if the action is for an amount that is within the monetary jurisdiction of the Small Claims Court, as set out in section 23 of the Courts of Justice Act, to a deputy judge of that Court or to the Small Claims Court Administrative Judge.

(2)  Subsection 58 (1.1) of the Act is repealed and the following substituted:

Notice

(1.1)  Notice of a motion for a reference under clause (1) (b) or (c) shall be given to every person specified by the procedures prescribed for the purposes of this Part.

(3) Subsection 58 (3) of the Act is amended by striking out “to a case management master or to a person agreed on by the parties” at the end and substituting “to a case management master, to a person agreed on by the parties or, if the action is for an amount that is within the monetary jurisdiction of the Small Claims Court, as set out in section 23 of the Courts of Justice Act, to a deputy judge of that Court or to the Small Claims Court Administrative Judge”

(4) Section 58 of the Act is amended by adding the following subsection:

Powers of Small Claims Court judge

(4.2) Subsection (4) also applies to a deputy judge of the Small Claims Court or to the Small Claims Court Administrative Judge, if a reference is directed to him or her.

(5) Subsection 58 (5) of the Act is amended by striking out “Where under subsection (1) the action has been referred to a master, to a case management master or to a person agreed on by the parties for trial” at the beginning and substituting “If all or part of an action is referred for trial under subsection (1)”.

44 (1) The French version of clause 60 (2) (b) of the Act is amended by striking out “le local, si le privilège grève celui-ci” and substituting “les lieux, si le privilège grève ceux-ci”.

(2) Clause 61 (5) (a) of the Act is amended by striking out “if there was no dispute at the meeting to a claim for lien” and substituting “if there was no dispute at the settlement meeting”.

(3) Sections 59 to 61 of the Act are repealed.

45 (1) Clause 62 (1) (b) of the Act is amended by striking out “on a reference by a master, by a case management master, or by a person agreed on by the parties” at the end and substituting “on a reference under section 58”.

(2) Clause 62 (6) (b) of the Act is amended by striking out “Arbitrations Act” at the end and substituting “Arbitration Act, 1991”.

46 Sections 66 and 67 of the Act are repealed.

47 (1) The heading to Part IX of the Act is repealed and the following substituted:

part ix
appointment of trustee

(2) Subsection 68 (4) of the Act is amended by striking out “mortgage, charge, interest” and substituting “mortgage, interest”.

48 Section 69 of the Act is repealed.

49 (1) Subsection 71 (1) of the Act is amended by striking out “Subject to subsection (3)” at the beginning and substituting “Except as otherwise provided in this section”.

(2) Subsection 71 (3) of the Act is repealed and the following substituted:

No appeal without leave

(3) No appeal lies from an interlocutory order made by the court, except with leave of the Divisional Court.

No appeal

(4) No appeal lies from a judgment or an order on a motion to oppose confirmation of a report under this Act, if the amount claimed is $10,000 or less.

50 Section 72 of the Act is amended by striking out “non-completion or abandonment” and substituting “non-completion, abandonment or termination”.

51 The French version of subsection 75 (2) of the Act is amended by striking out “sa réclamation de privilège” at the end and substituting “sa revendication de privilège”.

52 Section 76 of the Act is amended by striking out “Where a claim for lien is preserved by registration” at the beginning and substituting “Where a lien is preserved by registration of a claim for lien”.

53 (1) The French version of clauses 78 (4) (a) and (6) (a) of the Act is amended by striking out “le local était grevé” wherever it appears and substituting in each case “les lieux étaient grevés”.

(2) Subsection 78 (10) of the Act is amended by striking out “in a form prescribed” in the portion after clause (b) and substituting “in the prescribed form”.

54 The French version of section 82 of the Act is amended by striking out “le même local” in the portion before clause (a) and substituting “les mêmes lieux”.

55 The French version of section 83 of the Act is repealed and the following substituted:

Affectation du produit d’une assurance

83 Si des lieux grevés d’un privilège sont détruits en totalité ou en partie, le montant du produit d’une assurance à l’égard des lieux que reçoit le propriétaire ou le créancier hypothécaire est substitué aux lieux ainsi détruits et est réparti conformément à l’ordre de priorité établi à la présente partie.

56 The Act is amended by adding the following Part:

part xi.1
surety bonds

Bonds and public contracts

Definition

85.1 (1) In this section,

“public contract” means a contract between an owner and a contractor respecting an improvement, if the owner is the Crown, a municipality or a broader public sector organization.

Application

(2) Subject to the regulations, this section applies to a public contract if the contract price exceeds the amount prescribed for the applicable owner.

Exception

(3)  This section does not apply in the case of a contractor who is an architect or an engineer.

Requirement for labour and material payment bond

(4) On entering into a public contract, a contractor shall furnish the owner with a labour and material payment bond, in the prescribed form, that,

(a)	is of an insurer licensed under the Insurance Act to write surety and fidelity insurance;

(b)	has a coverage limit of at least 50 per cent of the contract price, or such other percentage of the contract price as may be prescribed; and

(c)	extends protection to subcontractors and persons supplying labour or materials to the improvement.

Requirement for performance bond

(5) On entering into a public contract, a contractor shall furnish the owner with a performance bond, in the prescribed form, that,

(a)	is of an insurer licensed under the Insurance Act to write surety and fidelity insurance; and

(b)	has a coverage limit of at least 50 per cent of the contract price, or such other percentage of the contract price as may be prescribed.

Claims process

(6) A bond form prescribed for the purposes of subsection (4) or (5) may set out the claims process applicable in respect of the bond.

No limitation on other bonds or security

(7) For greater certainty, this section does not limit the ability of the owner to require the contractor to provide other types of bonds or security.

Rights of action

Default, labour and material payment bond

85.2 (1) If a labour and material payment bond is in effect in respect of an improvement and the principal on the bond defaults in making a payment guaranteed by the bond, any person to whom the payment is guaranteed has a right of action to recover the amount of the person’s claim, in accordance with the terms and conditions of the bond, against the surety and the principal.

Default, performance bond

(2) If a performance bond is in effect in respect of an improvement and the contractor defaults in performing the contract guaranteed by the bond, the owner has a right of action to enforce the bond, in accordance with its terms and conditions, against the surety and the contractor.

Saving

(3) Nothing in this section makes the surety liable for an amount in excess of the amount that the surety undertakes to pay under a bond, and the surety’s liability under the bond shall be reduced by and to the extent of any payment made in good faith by the surety either before or after judgment is obtained against the surety.

Same

(4) Nothing in this section makes the surety liable as the principal under a bond, or makes the surety a party to any contract.

Subrogation

(5) On satisfaction of its obligation to any person under a bond to which this section applies, the surety shall be subrogated to all the rights of that person.

57 (1) Subsection 86 (1) of the Act is amended by striking out “settlement meeting” in the portion before clause (a) and substituting “any other step in a proceeding under this Act”.

(2) Subclause 86 (1) (b) (i) of the Act is repealed and the following substituted:

(i)	knowingly participated in the preservation or perfection of a lien, or represented a party at the trial of an action, where it is clear that the claim for a lien is without foundation, is frivolous, vexatious or an abuse of process, or is for a wilfully exaggerated amount, or that the lien has expired, or

(3) Subsection 86 (1) of the Act is amended by striking out “including where the motion is heard by, or the action has been referred under section 58 to, a master, case management master or commissioner” at the end and substituting “including where the motion is heard by a person other than a judge or the action has been referred under section 58”.

58 Section 87 of the Act is amended by adding the following subsections:

Exception, written notice of lien

(1.1)  Despite subsection (1), a written notice of lien shall be served in a manner permitted under the rules of court for service of an originating process.

Claim for lien to municipality

(1.2)  If the regulations so provide, a copy of a claim for lien shall, despite subsection (1), be given to the clerk of a municipality under subsection 34 (3.1) electronically in accordance with the regulations.

59 The Act is amended by adding the following section:

Financial Administration Act

87.1 If a ministry or specified public entity, as defined in the Financial Administration Act, is liable to pay interest under this Act, the payment of the interest is deemed to have been authorized and directed by the Treasury Board under section 11.4.1 of that Act.

60 The Act is amended by adding the following section:

Courts of Justice Act

87.2 In the event of a conflict between this Act and the Courts of Justice Act, this Act prevails to the extent of the conflict.

61 (1)  The Act is amended by adding the following section:

Transition, Construction Lien Amendment Act, 2017

87.3  (1)  This Act, as it read immediately before the day subsection 2 (2) of the Construction Lien Amendment Act, 2017 came into force, continues to apply with respect to an improvement if,

(a)	a contract for the improvement was entered into before that day, regardless of when any subcontract under the contract was entered into;

(b)	a procurement process, if any, for the improvement was commenced before that day by the owner of the premises; or

(c)	the premises is subject to a leasehold interest, and the lease was first entered into before that day.

Examples, procurement process

(2)  For the purposes of clause (1) (b), examples of the commencement of a procurement process include the making of a request for qualifications, a request for proposals or a call for tenders.

(2)  Section 87.3 of the Act, as enacted by subsection (1), is amended by adding the following subsection:

Same

(3)  Parts I.1 and II.1 apply in respect of contracts entered into on or after the day subsection 11 (1) of the Construction Lien Amendment Act, 2017 comes into force, and in respect of subcontracts made under those contracts.

62 (1) Section 88 of the Act is repealed and the following substituted:

Regulations

88 (1) The Lieutenant Governor in Council may make regulations respecting any matter necessary or advisable to carry out effectively the intent and purpose of this Act, including regulations,

(a)	respecting anything that, under this Act, may or must be prescribed or done by regulation;

(b)	prescribing forms and providing for their use.

Same, transitional matters

(2) The Lieutenant Governor in Council may make regulations providing for such transitional matters as the Lieutenant Governor in Council considers necessary or advisable in connection with the implementation of the Construction Lien Amendment Act, 2017.

(2) Subsection 88 (1) of the Act is amended by adding the following clauses:

(c)	for the purposes of subsection 1.1 (5), providing for modifications in the application of portions, provisions or regulations listed in that subsection;

(d)	governing the registry required to be established under clause 13.3 (1) (c);

(e)	governing fees that may be set by the Authorized Nominating Authority under clause 13.3 (2) (a) or that the Authority may determine under clause 13.10 (2) (b);

(f)	for the purposes of section 13.4, prescribing fees for the training and qualification of persons as adjudicators and for the appointment of adjudicators, and requiring their payment;

(g)	establishing procedures for the making of complaints against the Authorized Nominating Authority;

(h)	governing adjudication procedures for the purposes of subsection 13.6 (2);

(i)	governing the procedures for requiring a consolidated adjudication under subsection 13.8 (2);

(j)	governing procedures that apply if an adjudicator fails to complete an adjudication under Part II.1;

(k)	providing that Parts I.1 and II.1 do not apply with respect to the classes of contracts and subcontracts for improvements to land used in connection with a facility referred to in the definition of “nuclear facility” in the Nuclear Safety and Control Act (Canada) that are specified by the regulations.

(3) Subsection 88 (1) of the Act is amended by adding the following clause:

(l)	for the purposes of Part VIII, governing procedures that apply to actions.

(4) Subsection 88 (1) of the Act is amended by adding the following clause:

(m)	exempting public contracts from the application of section 85.1.

(5) Section 88 of the Act is amended by adding the following subsection:

Conflict

(1.1) In the event of a conflict between a regulation made under clause 88 (1) (l) and the Courts of Justice Act or the rules of court, the regulation prevails to the extent of the conflict.

63 The French version of the following provisions of the Act is amended by striking out “l’avis de privilège” wherever it appears and substituting in each case “la revendication de privilège”:

1.	Subsection 19 (4).

2.	Clause 34 (1) (b).

3.	Subsections 34 (3) and (4).

4.	Subsection 34 (5), in the portion before clause (a).

5.	Subsection 40 (1), in the portion before paragraph 1.

6.	Subsection 40 (2).

7.	Clause 40 (3) (b).

8.	Clause 41 (1) (b).

9.	Clauses 44 (1) (b) and (c).

10.	Subsection 44 (2).

11.	Subsection 45 (1), in the portion before clause (a).

12.	Clause 45 (1) (c), in the portion before subclause (i).

13.	Subsection 46 (1).

14.	Subclause 47 (1) (b) (i).

15.	Subclause 86 (1) (b) (i).

64 The French version of the following provisions of the Act is amended by striking out “d’un avis de privilège” wherever it appears and substituting in each case “d’une revendication de privilège”:

1.	Clause 34 (1) (a).

2.	Clause 44 (1) (a).

65 The French version of the following provisions of the Act is amended by striking out “la formule prescrite” wherever it appears and substituting in each case “le formulaire prescrit”:

1.	Subsection 31 (5), in the portion before clause (a).

2.	Paragraph 1 of subsection 32 (1).

3.	Subsection 33 (1).

4.	Subsection 33.1 (3), in the portion before clause (a).

5.	Clause 36 (3) (a).

6.	Clauses 41 (1) (a) and (b).

7.	Section 42.

8.	Section 43.

9.	Clauses 62 (1) (a) and (b).

10.	Subsection 62 (2).

66 The French version of the following provisions of the Act is amended by striking out “des services et des matériaux” wherever it appears and substituting in each case “des services ou des matériaux”:

1.	Clause (b) of the definition of “price” in subsection 1 (1).

2.	Subsection 2 (2).

3.	Subsection 8 (1), in the portion after clause (b).

4.	Subsection 8 (2).

5.	Subsection 11 (1).

6.	Subsection 14 (1).

7.	Subsections 22 (1) and (2).

8.	Subsection 24 (1).

9.	Clause 31 (2) (b), in the portion before subclause (i).

10.	Subsection 31 (5), in the portion before clause (a).

11.	Subsection 34 (7).

12.	Section 72.

67 The French version of the following provisions of the Act is amended by striking out “aux services et aux matériaux” wherever it appears and substituting in each case “aux services ou aux matériaux”:

1.	Subsection 17 (1).

2.	Section 21.

3.	Subsections 31 (1) and (4).

68 The French version of the following provisions of the Act is amended by striking out “les services et les matériaux” wherever it appears and substituting in each case “les services ou les matériaux”:

1.	Subsection 34 (1), in the portion before clause (a).

2.	Section 48.

69 The French version of the following provisions of the Act is amended by striking out by striking out “des matériaux ou des services” wherever it appears and substituting in each case “des services ou des matériaux”:

1.	Section 4.

2.	Subclause 82 (a) (ii).

70 The French version of the following provisions of the Act is amended by striking out “le local” wherever it appears and substituting in each case “les lieux”:

1.	The definition of “owner” in subsection 1 (1).

2.	Subsection 3 (1).

3.	Clause 9 (1) (b).

4.	Subsection 23 (1).

5.	Clause 32 (2) (e).

6.	Clauses 34 (1) (a) and (b).

7.	Subclause 34 (5) (e) (i).

8.	Clauses 36 (3) (a) and (b).

9.	Clause 39 (2) (a).

10.	Subsection 40 (2).

11.	Clause 40 (3) (b).

12.	Clauses 41 (1) (a) and (b).

13.	Clauses 44 (1) (a) and (b).

14.	Subsections 44 (3) and (6).

15.	Subsections 45 (1), in the portion before clause (a), and 45 (2).

16.	Subsections 46 (1) and (2).

17.	Section 49.

18.	Clauses 60 (2) (c) and (d).

19.	Subsection 60 (3).

20.	Subsection 62 (5).

21.	Section 64.

22.	Subsections 65 (1) and (2).

23.	Subsections 68 (1) and (4).

24.	Clause 68 (2) (a).

25.	Subsection 78 (1).

26.	Subsection 78 (3), in the portion before clause (a).

27.	Subsection 78 (4), in the portion before clause (a).

28.	Subsection 78 (5).

29.	Subsection 78 (6), in the portion before clause (a).

30.	Clause 78 (7) (a).

31.	Subsection 78 (8), in the portion before clause (a).

32.	Subsection 78 (10), in the portion before clause (a).

33.	Subsection 80 (2).

34.	Section 84.

35.	Clause 87 (1) (b).

71 The French version of the following provisions of the Act is amended by striking out “du local” wherever it appears and substituting in each case “des lieux”:

1.	The definition of “written notice of a lien” in subsection 1 (1).

2.	Clause 1 (2) (b).

3.	Subsection 19 (3).

4.	Clause 32 (2) (f).

5.	Clause 34 (1) (a).

6.	Subsection 34 (3).

7.	Clause 34 (5) (a).

8.	Clause 34 (5) (e), in the portion before subclause (i).

9.	Clause 36 (3) (a).

10.	Subparagraph 3 i of subsection 39 (1).

11.	Paragraphs 1, 2 and 3 of subsection 44 (9).

12.	Section 49.

13.	Subsection 53 (1).

14.	Clause 68 (2) (c).

15.	Clause 78 (3) (a).

16.	Subsection 80 (2).

17.	Clause 82 (b).

72 The French version of the following provisions of the Act is amended by striking out “locaux” wherever it appears and substituting in each case “lieux”:

1.	Subsection 20 (1).

2.	Subsection 34 (7).

3.	Subsection 36 (5).

4.	Section 42.

5.	Subsection 44 (4).

6.	Subsections 74 (1) and (2).

7.	Subclause 82 (a) (ii).

73 The French version of the following provisions of the Act is amended by striking out “est situé le local ou une partie de celui-ci” wherever it appears and substituting in each case “sont situés les lieux ou une partie de ceux-ci”:

1.	Clause 58 (1) (a).

2.	Subsection 58 (3).

Complementary Amendments to Other Acts

Condominium Act, 1998

74 (1) Sections 13 and 14 of the Condominium Act, 1998 are repealed and the following substituted:

Effect on encumbrances

13 (1) Upon the registration of the declaration and description of a corporation that is not a common elements condominium corporation, an encumbrance against the common elements registered before the registration of the declaration and description is no longer enforceable against the common elements but is enforceable against all the units and common interests.

Same, common elements condominium corporation

(2) Upon the registration of the declaration and description of a common elements condominium corporation, an encumbrance against the common elements registered before the registration of the declaration and description is no longer enforceable against the common elements but is enforceable against all the parcels of land mentioned in subsection 139 (1) and common interests.

Encumbrances on or after declaration

(3) An encumbrance against the common elements on or after the registration of the declaration and description of a corporation is not enforceable against the common elements but is enforceable against all the units and common interests or, in the case of a common elements condominium corporation, against all of the parcels of land and common interests.

Discharge of encumbrance

14 (1) If an encumbrance is, by virtue of subsection 13 (1) or (3), enforceable against all the units and common interests, an owner may discharge the portion of the encumbrance that is applicable to the owner’s unit and common interest by paying to the encumbrancer the portion of the amount owing on account of principal and interest under the encumbrance that is attributable to the owner’s common interest as specified in the declaration.

Same, common elements condominium corporation

(2) If an encumbrance is, by virtue of subsection 13 (2) or (3), enforceable against all the parcels of land mentioned in subsection 139 (1) and common interests, an owner may discharge the portion of the encumbrance that is applicable to the owner’s parcel of land and common interest by paying to the encumbrancer the portion of the amount owing on account of principal and interest under the encumbrance that is attributable to the owner’s common interest as specified in the declaration.

Form

(3) Upon payment of the portion of the encumbrance described in subsection (1) or (2), and upon demand, the encumbrancer shall give to the owner a discharge of the owner’s unit or parcel of land, as the case may be, and common interest, in accordance with the requirements of the regulations made under this Act.

Exception, construction lien

(4) Subsections (1), (2) and (3) do not apply if the encumbrance is a lien under the Construction Act.

(2) Subsection 14 (3) of the Act, as enacted by subsection (1), is amended by striking out “the regulations made under this Act” at the end and substituting “the regulations”.

Courts of Justice Act

75 Subsection 103 (3) of the Courts of Justice Act is amended by striking out “Construction Lien Act” at the end and substituting “Construction Act”.

Land Titles Act

76 (1) Section 104 of the Land Titles Act is amended by striking out “Construction Lien Act” and substituting “Construction Act”.

(2) Subsection (1) applies only if it comes into force before section 61 of Schedule 28 to the Strong Action for Ontario Act (Budget Measures), 2012 comes into force.

(3) Section 104 of the Act, as re-enacted by section 61 of Schedule 28 to the Strong Action for Ontario Act (Budget Measures), 2012, is amended by striking out “Construction Lien Act” and substituting “Construction Act”.

Limitations Act, 2002

77 (1) The Schedule to the Limitations Act, 2002 is amended by striking out “Construction Lien Act” in the column titled “Act” and substituting “Construction Act”.

(2) The Schedule to the Act is amended by striking out “sections 31 and 36” in the column titled “Provision” and substituting “subsections 13.18 (2) and 13.20 (2) and sections 31 and 36”.

Mining Act

78 (1) Subsection 171 (1)  of the Mining Act is repealed and the following substituted:

Application of Construction Act

(1) Except as provided in this Act, the Construction Act applies to mines, mining claims, mining lands and connected works.

(2) Subsections 171 (2) and (3) of the Act are amended by striking out “Construction Lien Act” wherever it appears and substituting in each case “Construction Act”.

Ontario New Home Warranties Plan Act

79 Subsection 14 (5) of the Ontario New Home Warranties Plan Act is amended by striking out “Construction Lien Act” at the end and substituting “Construction Act”.

Protecting Condominium Owners Act, 2015

80 If, on the day this section comes into force, paragraph 6 of subsection 146 (1) of Schedule 1 to the Protecting Condominium Owners Act, 2015 is not yet in force, that paragraph is repealed.

Registry Act

81 (1) The French version of subsection 38 (3) of the Registry Act is amended by striking out “d’un certificat d’instance” and substituting “d’un certificat d’action” and by striking out “chaque privilège ou certificat d’instance” and substituting “chaque revendication de privilège et certificat d’action enregistré”.

(2) Subsection 38 (3) of the Act is amended by striking out “Construction Lien Act” and substituting “Construction Act”.

(3) The French version of clause 67 (1) (b) of the Act is amended by striking out “un avis d’un privilège” at the beginning and substituting “une revendication de privilège”.

(4) Subsection 67 (1) of the Act is amended by striking out “Construction Lien Act” wherever it appears and substituting in each case “Construction Act”.

Workplace Safety and Insurance Act, 1997

82 (1) The French version of subsection 142 (1) of the Workplace Safety and Insurance Act, 1997 is amended by striking out “d’un local” and substituting “de lieux”.

(2) The French version of subsection 142 (2) of the Act is amended by striking out “locaux” and substituting “lieux”.

(3) Subsections 142 (1) and (2) of the Act are amended by striking out “Construction Lien Act” wherever it appears and substituting in each case “Construction Act”.

S.O. 1993, c. 27

83 Paragraph 1 of section 8 of the Revised Statutes Confirmation and Corrections Act, 1993 is repealed.

S.O. 1994, c. 27

84 Subsection 42 (3) of the Statute Law Amendment Act (Government Management and Services), 1994 is repealed.

S.O. 1997, c. 23

85 Subsection 4 (2) of the Government Process Simplification Act (Ministry of the Attorney General), 1997 is repealed.

Commencement and Short Title

Commencement

86 (1) Subject to subsections (2), (3), (4), (5) and (6), this Act comes into force on the day it receives Royal Assent.

(2) The following provisions come into force on a day to be named by proclamation of the Lieutenant Governor:

1.	Section 1.

2.	Subsections 2 (1), (2), (3), (5), (7), (8), (12), (14), (16) and (17).

3.	Section 3.

4.	Subsections 4 (1), (2), (3), (4), (6) and (7) and 6 (2).

5.	Sections 7 and 8.

6.	Subsection 10 (2).

7.	Section 11.

8.	Subsections 13 (4), 14 (2) and (4), 16 (1) and (3), 17 (3) and 21 (2) and (3).

9.	Section 22.

10.	Subsections 23 (2) and (3).

11.	Section 24.

12.	Section 26, other than subsection (4).

13.	Sections 27 and 28.

14.	Subsections 29 (2), (4), (6), (10) and (11).

15.	Subsections 30 (2) and 31 (1).

16.	Subsections 32 (1), (2), (3), (4), (6), (7), (8) and (9).

17.	Section 33.

18.	Subsection 34 (2).

19.	Section 36, other than subsection (3).

20.	Section 37.

21.	Subsection 39 (2).

22.	Sections 40 and 41.

23.	Subsection 42 (2).

24.	Section 43.

25.	Subsection 44 (3).

26.	Subsection 45 (1).

27.	Section 46.

28.	Subsection 47 (1).

29.	Sections 48 to 50 and 56 to 61.

30.	Section 62, other than subsection (1).

31.	Subsection 74 (1).

32.	Section 75.

33.	Sections 77 to 79.

34.	Subsections 81 (2) and (4) and 82 (3).

(3) Subsection 74 (2) comes into force on the later of the day subsection 74 (1) comes into force and the day subsection 1 (15) of Schedule 1 to the Protecting Condominium Owners Act, 2015 comes into force.

(4) Subsections 76 (1) and (2) come into force on the day section 1 comes into force.

(5) Subsection 76 (3) comes into force on the later of the day section 1 comes into force and the day section 61 of Schedule 28 to the Strong Action for Ontario Act (Budget Measures), 2012 comes into force.

(6) Section 80 comes into force on the day subsection 74 (1) comes into force.

Short title

87 The short title of this Act is the Construction Lien Amendment Act, 2017.

| Français |  |
| --- | --- |

Back to top